## PI Schedule
Step | Purpose | Attendees | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 5 | IP Iteration
Strategic Themes & Portfolio Vision (Ongoing) | Ensure alignment of PI goals with business strategy | Portfolio Leadership, Business Owners, Product Management | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing
Epic Identification & Lean Business Case (1–2 PIs ahead) | Capture large initiatives and evaluate feasibility & value | Business Owners, Portfolio Management, Architects | Prior PI | Prior PI | Prior PI | Prior PI | Prior PI | If targeting next-next PI
Program Backlog Review & Approval | Validate readiness of features for PI Planning | Business Owners, Product Management, RTE, Architects |  |  | Set Business Objectives for upcoming PI | Each Team Receives a List of Features to be planned | (Teams break Features to Tasks) | (Teams Prep Draft Plan)
Epic → Feature Breakdown | Decompose epics into smaller, deliverable features | Product Management, Architects, Product Owners |  |  |  | X | X | X
Dependency Identification | Identify and track cross-team dependencies for delivery planning | Product Management, RTE, Architects, Product Owners |  |  |  |  | X | X
WSJF Prioritization | Rank features by value, time criticality, risk reduction, and effort | Product Management, Business Owners, Product Owners |  |  |  |  | X | X
Finalize Shortlist for Next PI | Confirm and lock the list of features for next PI | Product Management, Business Owners, RTE |  |  |  |  | ART review current PI | X
Inspect & Adapt | Review PI results, run problem-solving workshop, improve processes. | All teams, Business Owners, Product Manager, RTE | [5 empty] | (End of PI)
PI Planning (Next PI) | Align all teams on PI objectives, plan delivery, and manage dependencies | All ART teams, RTE, Product Management, Business Owners, Architects | [5 empty] | Start of quarter
ART Sync / Program Sync | Review PI progress, unblock cross-team dependencies, manage risks/scope. | RTE, Product Manager, Scrum Masters, Business Owners (optional), Architects | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing
Scrum of Srum | Align teams on PI Objectives, surface & resolve cross-team dependencies, address blockers, update Program Board | Scrum Masters, Release Train Engineer (RTE), occasionally Product Owners & Architects | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing

## PI Planning - Day 1
Time | Activity | Purpose | Attendees
09:00 – 09:30 | Business Context & Vision | Leadership explains business priorities, market updates, and vision for the PI. | Business Owners, Product Manager, RTE, All Teams
09:30 – 10:00 | Product/Solution Vision | Product Manager shares top features and objectives for the PI. | Product Manager, All Teams
10:00 – 10:30 | Architecture/UX Briefing | Architects present key enablers, tech constraints, and design standards. | Architects, All Teams
10:30 – 10:45 | Break | — | —
10:45 – 12:30 | Team Breakouts – Draft Planning | Teams draft their sprint plans, estimate capacity, identify dependencies. | All Teams
12:30 – 13:30 | Lunch | — | —
13:30 – 14:30 | Team Breakouts – Continue | Teams refine sprint plans and update backlog priorities. | All Teams
14:30 – 15:15 | Draft Plan Review (Round 1) | Each team presents draft PI objectives, risks, dependencies. | All Teams, RTE
15:15 – 15:30 | Break | — | —
15:30 – 16:30 | Management Review & Problem-Solving | Leadership, Product, and RTE address cross-team conflicts and risks. | RTE, Business Owners, Product Manager, Architects
16:30 – 17:00 | Wrap-up Day 1 | Summarize progress, open items, and expectations for Day 2. | RTE, All Teams

## PI Planning - Day 2
Time | Activity | Purpose | Attendees
09:00 – 09:45 | Team Breakouts – Final Adjustments | Finalize sprint plans, capacity, dependencies, risks. | All Teams
09:45 – 10:30 | Final Plan Review (Round 2) | Each team presents final PI objectives, dependencies, risks. | All Teams, RTE, Business Owners
10:30 – 10:45 | Break | — | —
10:45 – 11:15 | ROAM Risks | Classify each risk as Resolved, Owned, Accepted, or Mitigated. | All Teams, RTE
11:15 – 11:45 | Confidence Vote | Teams rate confidence; discuss low scores and adjust if needed. | All Teams, RTE
11:45 – 12:30 | Plan Rework (if needed) | Make last adjustments based on risk resolution and confidence vote. | Relevant Teams
12:30 – 13:15 | Lunch | — | —
13:15 – 14:00 | Final PI Commitments | Confirm objectives and commitment from each team. | All Teams
14:00 – 14:30 | Planning Retrospective | Capture feedback on the PI Planning process for improvement. | All Teams
14:30 – 15:00 | Closing Remarks & Next Steps | RTE summarizes plans, risks, and communication cadence. | RTE, Business Owners, Product Manager

## Program Board
Team | Iteration 1 Date | Iteration 2 Date | Iteration 3 Date | Iteration 4 Date | Iteration 5 Date | IP Iteration Date | Next PI |  | Feature 1
Scrum Team 1 | [7 empty] | StoryID | Story Description | Assignee
Scrum Team 2 | [7 empty] | 1 | Identify integration requirements | Team A
Scrum Team 3 | [7 empty] | 2 | Prepare integration environment | Team B
Scrum Team 4 | [7 empty] | 3 | Integrate | Team A
Middleware | [7 empty] | 4 | Test Results | Team A
Data Team
Story 1
Story 2
Story 3

## Team Iteration
Feature | Iteration 1 (1–14 Jul) | Iteration 2 (15–28 Jul) | Iteration 3 (29 Jul–11 Aug) | Iteration 4 (12–25 Aug) | Iteration 5 (26 Aug–8 Sep) | IP Iteration (9–30 Sep) |  |  | Feature 1
Feature 1 | [7 empty] | StoryID | Story Description | Assignee | Points | Dependency
Feature 2 | [7 empty] | 1 | Identify integration requirements | Team A | 3
Feature 3 | [7 empty] | 2 | Prepare integration environment | Team B | 5 | task 1
Feature 4 | [7 empty] | 3 | Integrate | Team A | 8
Feature 5 | [7 empty] | 4 | Test Results | Team A | 2 | task 2, task 3
Feature 6
| Capacity:80 | Capacity: | Capacity: | Capacity: | Capacity:
| Load:120 | Load: | Load: | Load: | Load:
Probability and Impact
[9 empty] | Team: | Team A
Each Team aim ti complete 6 to 10 Features | [8 empty] | Impact: | Mild
[9 empty] | Probability : | Low
[9 empty] | Risk Description Cause | Delay in Team B in preparing the interation environments
[9 empty] | Risk: | Delay in delivering Feature 1
Impact:
Probability and Impact Matrix
High
Prob
Low
[9 empty] | Impact | High
Story 1
Story 3
Story 4
Feature 1 Team B delay
Feature 2 Team B,C delay

## ART Sync Meeting
Section | Purpose | Who Speaks | Visual / Tool
1. Welcome & Agenda (2–3 min) | Set context, review agenda & timebox | RTE | Agenda slide
2. PI Progress Overview (5–8 min) | Show overall PI burn-up, % complete, and trends | RTE / PM | Program Board or Jira Dashboard
3. Team Updates (2–3 min per team) | - Progress on committed objectives- Key achievements- Risks & blockers- Upcoming iteration focus | Scrum Masters / POs | Iteration board with RAG status
4. Dependencies (5 min) | Review open dependencies, due dates, and resolutions | Teams / RTE | Dependency tracker table
5. Risks & Issues (ROAM) (5 min) | Review newly raised risks, update ROAM log | All | Risk board
6. Scope Changes (3–5 min) | Review new scope, descoped work, and impacts on PI commitments | Product Manager | Backlog delta view
7. Decisions & Actions (3 min) | Assign owners, set due dates | RTE | Action tracker
8. Wrap-up (1–2 min) | Confirm next sync, key follow-ups | RTE | Agenda slide

## Team Objective Board
Team Name | Objective Type | PI Objective | Business Value (1-10) | Linked Features / Stories | Dependencies | RAG Status | Risks / Assumptions
Team Phoenix | Committed | Improve page load time by 40% | 9 | F-1023, S-2105 | Team Atlas for API updates | Green | API updates completed on time
Team Phoenix | Committed | Implement secure payment gateway | 10 | F-1088, S-2110 | Vendor for payment gateway certification | Green | Payment provider meets compliance deadlines
Team Phoenix | Committed | Enhance mobile app user onboarding | 8 | F-1044, S-2120 | UX Team for onboarding design assets | Amber | Design assets ready by Iteration 2
Team Phoenix | Stretch | Migrate all historical data to new reporting system | 6 | F-1099, S-2130 | Data Team for access to historical datasets | Amber | Data cleansing completed before migration
Team Phoenix | Stretch | Introduce AI-powered product recommendations | 5 | F-1102, S-2145 | Recommendation Engine vendor integration | Red | Vendor delivers engine by Iteration 4

## ROAM Board
Resolved | Owned | Accepted | Mitigated | Resolved – Fully addressed during planning.
Sticky note #1 | Sticky note #2 | Sticky note #3 | Sticky note #4 | Owned – Someone is accountable to manage and resolve after PI Planning.
Sticky note #5 | Sticky note #6 | Sticky note #7 | Sticky note #8 | Accepted – Acknowledged and accepted with no further action.
Mitigated – Steps identified to reduce impact or likelihood.

## ART Sync Board
Date | Team Name | Iteration | Feature | Stories Planned | Stories Completed | Progress % | RAG Status | Key Achievements | Risks / Blockers | Dependency | Scope Changes | Next Iteration Focus
2025-08-12 | Team Phoenix | Iteration 3 | Secure Payment Gateway | 20 | 15 | 75 | Amber | Payment gateway integration 80% done | API vendor delay may impact completion | Depends on Vendor X API release | Added fraud detection feature | Finalize payment gateway testing
2025-08-12 | Team Atlas | Iteration 3 | Vendor API Integration | 18 | 16 | 89 | Green | Vendor API integration completed; Reporting module in QA | None | None | None | Deploy reporting module to production
2025-08-12 | Team Orion | Iteration 3 | Auth Module Refactor | 22 | 18 | 82 | Amber | Auth module refactor 90% complete | UX team delay in onboarding assets | Depends on UX team asset delivery | Onboarding redesign requested | Complete onboarding flow and start UAT

## Jira Story Mapping
SAFe Level | Definition | Jira Equivalent (Standard) | Jira Equivalent (with Advanced Roadmaps / Jira Align) | Typical Owner
Portfolio Epic | Large business initiative spanning multiple PIs and ARTs | No default field → often tracked manually or as a custom “Portfolio Epic” issue type | Initiative or Portfolio Epic | Business Owners / Portfolio Mgr
Capability (optional) | Higher-level solution functionality across ARTs | No default field (often skipped in Jira unless using SAFe in Jira) | Capability (custom issue type in Jira Align) | Solution Management / Architects
Feature | Service / function that delivers value in a PI | Epic | Feature (custom issue type in Jira Align) | Product Manager
Story | Smallest customer value slice, completed in an iteration | Story or Task | Story | Product Owner / Team
Enabler (Task) | Technical work enabling future value delivery | Task issue type | Same, or Enabler custom type | Architects / Tech Leads
PI Objective | Business or technical goal for a PI | No direct Jira issue type → tracked in Confluence or Excel | Objective (in Jira Align) | Product Manager / Teams